## 1b) Project Portfolio
PROJECT PORTFOLIO - LIST OF POTENTIAL PROJECTS AWAITING SIGN OFF, BUSINESS CASE ALREADY DRAFTED
Project ID | Potential Project/Programme | Business Area | Strategic Objective (order of importance in brackets) Quick ROI - within 6 months (1) Risk Avoidance/Regulatory (2) Improved Customer Experience (3) Longer ROI - 12 months + (4) | Additional Comments
P001 | National Marketing Campaign (Billboards & Bus Shelters) | Marketing | 4
P002 | Customer Loyalty Programme | Customer | 3
P003 | Warehouse Expansion Programme | Warehouse | 4 | Costly project with a long timeline, 24 month project
P004 | Data Protection Process Improvements | Audit | 2
P005 | CRM System | Customer | 3 | Costly project, requires integrations with web and app
P006 | Email Receipts | Customer | 1
P007 | Social Media Management Tool | Customer | 1
P008 | Finance Software Upgrade | Finance | 4
P009 | Warehouse AI System | Warehouse | 4
P010 | Till System Upgrade | Stores | 4

## 2) Kanban Board
KANBAN BOARD - APP REFRESH PROJECT
TO DO | IN PROGRESS | DONE | NEXT SPRINT | FUTURE WORK
Demo software in place
CRM fields created
Customer account creation - ability to save favourite products
Product numbers created in app
Payment (card) connected to finance system
Payment facility (card) implemented in app
Payment facility (paypal) implemented and connected to finance system
Extra product lines added to app
Store location software updated
Navigate any store using the app
BBC News live feed built into app
Social media feeds updated in app
Email collector for newsletter feed updated
Finance reporting feed developed
Finance reporting feed tested
QR code for product offers
App design complete UX
App design complete UI
App design A/B testing
Gaming built into app
App support process documented
App backup process documented (Disaster recovery)
App backup process tested (Disaster recovery)
App information security - features identified
App information security - features built
Sync with website in place

## 2) Kanban Board.
KANBAN BOARD - APP REFRESH PROJECT
TO DO | DONE | NEXT SPRINT | FUTURE WORK
Product Development Swim Lane
Demo software in place
CRM fields created
Customer account creation - ability to save favourite products
Product numbers created in app
Extra product lines added to app
QR code for product offers
Sync with website in place
Payment and Finance Swim Lane
Payment (card) connected to finance system
Payment facility (card) implemented in app
Payment facility (paypal) implemented and connected to finance system
Finance reporting feed developed
Finance reporting feed tested
App Design and UX/UI Swim Lane
App design complete UX
App design complete UI
App design A/B testing
Store Operations Swim Lane
Store location software updated
Navigate any store using the app
Marketing and Communication Swim Lane
Email collector for newsletter feed updated
App Support and Security Swim Lane
App support process documented
App backup process documented (Disaster recovery)
App backup process tested (Disaster recovery)
App information security - features identified
App information security - features built
Out of Scope
BBC News live feed built into app
Social media feeds updated in app
Gaming built into app

## 3) Risk Log
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 | 2023-05-01 | Information Security Compliance: The audit findings indicate concerns regarding data protection and information security compliance across multiple projects, including the App Refresh project. Failure to address these concerns may result in penalties, fines, and reputational damage | 5 | 5 | 25 | Conduct a thorough review of data protection and information security requirements for all projects | 2023-05-11 | Project Manager/Audit Lead | Complete information security related developments before the external audit visit in 2 weeks.
R002 | 2023-05-01 | Resource Allocation: The Website Refresh project is utilizing more UX/UI team time than initially agreed upon. This could create resource constraints and affect the progress of the App Refresh project if the shared resources are not properly managed. | 3 | 3 | 9 | Communicate the importance of complying to agreed upon resource allocations to avoid potential conflicts and delays | 2023-05-03 | Project Manager | Revisit resource allocation agreements and ensure proper resource balancing between projects
R003 | 2023-05-01 | Developer Dependencies: The project relies on developers having access to key development tools. Delays in obtaining necessary licenses or dependencies on specialized expertise can impact backlog items, testing, and deployment of features, potentially leading to project delays | 3 | 3 | 9 | There is need to prioritize obtaining necessary licenses and resolving dependencies early in the project | 2023-05-02 | Project Manager | Resolve license and expertise dependencies as soon as possible to minimize delays of project completion
R004 | 2023-05-03 | Time Constraints: The project follows an agile approach with short delivery timelines. However, delays in development, testing, or deployment due to resource constraints, technical challenges, or unexpected issues may risk meeting the project deadlines. | 3 | 3 | 9 | Ensure clear communication and expectations with the development team about project timelines and priorities and avoid time wasting | 2023-05-14 | Project Manager | Time is a valuable asset and should make use of it
R005 | 2023-05-03 | Testing and Quality Assurance: The absence of the Test Lead during Sprint 3 can impact the testing process, potentially resulting in delayed bug identification, fixing, and overall quality assurance of the app. | 3 | 2 | 6 | Hire and get a temporary replacement or backup resource for the Test Lead during their absence in Sprint 3 | 2023-05-12 | Project Manager/Scrum Master | The project requires staff to be proactive and ensure quality assurance
R006 | 2023-05-03 | Lack of Specialization in Information Security: Developers have expressed concerns about information security development, as they are not specialists in this area. This knowledge gap may lead to inadequate implementation of security measures, potentially exposing the system and data breaches. | 3 | 2 | 6 | Should consider involving information security specialists or consultants to provide guidance and support to the development team | 2023-05-14 | Project Manager | For the project to be a success, the whole team should be fully equiped with necessary resources
R007 | 2023-05-03 | Deviation from Product Roadmap: Developer's appetite for creating new features may lead to scope creep, with the inclusion of items that are not relevant to the project's goal. This can result in the project losing focus and potentially impacting the timely delivery of the project | 2 | 3 | 6 | Maintain clear and open communication with the development team to ensure that they won't deviate from the project's goals and roadmap | 2023-05-14 | Project Manager/Product Owner | Communication is the key to delivering project without compromising overall scope
R008 |  |  |  |  | 0
R009 |  |  |  |  | 0
R010 |  |  |  |  | 0
R011 |  |  |  |  | 0
R012 |  |  |  |  | 0
R013 |  |  |  |  | 0
R014 |  |  |  |  | 0
R015 |  |  |  |  | 0
R016 |  |  |  |  | 0
R017 |  |  |  |  | 0
R018 |  |  |  |  | 0
R019 |  |  |  |  | 0
R020 |  |  |  |  | 0
R021 |  |  |  |  | 0
R022 |  |  |  |  | 0
R023 |  |  |  |  | 0
R024 |  |  |  |  | 0
R025 |  |  |  |  | 0

## 4) Issue Log
ISSUE LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the issue is and what it is impacting - time, budget or quality) | Impact Rating (Enter 1-5) | Issue RAG | Action & Owner (What needs to happen to resolve this issue?) | Target Action Completion Date (When will actions be completed by?) | Issue Owner (Who is responsible for resolving this issue?) | Any Additional Comments / Any Escalation Required?
I001 | 2023-05-02 | Competing Roadmap Priorities: The business teams have different priorities and want all roadmap items to be developed simultaneously, creating a challenge in resource allocation and communication | 5 | 5 | Prioritize and sequence roadmap items based on strategic objectives, business value, and available resources. There is a need to communicate with stakeholders on priorities and manage expectations | 2023-05-14 | Project Manager | Make sure there's effective resource planning and allocation to meet the project's goals
I002 | 2023-05-02 | Resource Constraints and Dependencies: Some developers lack necessary tool licenses, and the Test Lead is on leave, resulting in delays in development, testing, and deployment of features The project's timeline may be affected due to delayed development and testing. Budget may be impacted if additional resources or licenses are required. Quality could suffer if rushed testing leads to bugs and issues | 5 | 5 | Explore options to obtain the required tool licenses. Allocate resources effectively and communicate and coordinate with other project teams to manage dependencies. Provide guidance and support to developers and ensure adequate testing coverage | 2023-05-14 | Project Manager/Scrum Master | Failure to address these issues will result in project failure and wastage of resources
I003 | 2023-05-02 | Information Security and Data Protection Non-Compliance: Non-compliance with data protection and information security regulations have been identified, risking penalties and potential security breaches. Non-compliance issues may lead to additional efforts, costs, and potential legal consequences. It could result in delays if security related development tasks are not completed before the external audit | 5 | 5 | Meet with the Audit Lead to discuss findings and develop an action plan to address non-compliance issues. Prioritize information security-related development tasks and ensure their completion before the external audit. Communicate the importance of data protection and security to the project team and implement necessary measures to achieve compliance | 2023-05-10 | Project Manager/ Audit Lead | Without meaningful data protection methods can jeopardize the quality of information
I004 | 2023-05-04 | Lack of Clarity in Project Direction: There is a lack of clarity amongst the business teams regarding project priorities and objectives. Lack of clarity can lead to delays in decision-making, and potential rework, impacting time and budget. It may also result in lower-quality deliverables if requirements and expectations are not well-defined | 3 | 3 | Facilitate discussions with the Product Owner and stakeholders to clarify project priorities and objectives. Come up with a roadmap that reflects business needs and feasibility. Provide clear guidance to the development team and conduct regular communication on the project goal and product roadmap | 2023-05-14 | Product Owner/Project Manager | As an Agile PM, you should be able to demonstrate control and lead the team to achieve the best results
I005 | 2023-05-05 | Website Project Resource Allocation: The Website Project Manager is utilizing more UX/UI team time than agreed, potentially affecting resource availability for the App Refresh project.The increased allocation of resources to the Website project may lead to delays or compromised quality for the App Refresh project, as there may not be sufficient resources available for its timely completion | 3 | 3 | Review and adjust resource allocation for the UX/UI team to ensure a balanced distribution between the App Refresh and Website Refresh projects. Coordinate with the Website Project Manager to optimize resource utilization while meeting project deadlines and objectives. Communicate and put resource needs with the stakeholders | 2023-05-14 | Project Manager/ Website Project Manager | Following the Agile principle. It clearly emphasizes on delivery of project resources on time and avoiding any unnecessary delays
I006 |  |  |  | 0
I007 |  |  |  | 0
I008 |  |  |  | 0
I009 |  |  |  | 0
I010 |  |  |  | 0
I011 |  |  |  | 0
I012 |  |  |  | 0
I013 |  |  |  | 0
I014 |  |  |  | 0
I015 |  |  |  | 0
I016 |  |  |  | 0
I017 |  |  |  | 0
I018 |  |  |  | 0
I019 |  |  |  | 0
I020 |  |  |  | 0
I021 |  |  |  | 0
I022 |  |  |  | 0
I023 |  |  |  | 0
I024 |  |  |  | 0
I025 |  |  |  | 0

## 5) Sprint 1 - Planned vs Actual
|  | Dev 1 | Dev 2 | Dev 3 | Dev 4 | Tester
| Planned | 10 | 10 | 8 | 12 | 10
| Actual | 5 | 10 | 8 | 20 | 11
Questions for the Scrum Master
1. What factors contributed to the discrepancy between the planned and actual number of testers in the last sprint?
2. Why did the number of tasks in dev4 exceed the planned count? Were there any specific challenges or unexpected issues? (Unknown Unknowns)
3. Were there any specific reasons why the number of tasks in dev1 was lower than planned? Did this impact the progress or completion of backlog items?
4. What were the reasons behind the consistent match between the planned and actual number of tasks in dev3 and dev2?
5. Can you provide any information on the impact of the variances on the overall sprint progress and the completion of backlog items?
6. How did the variances in the Planned vs Actual chart affect the testing phase of the project? Were there any delays or challenges?
7. What steps have been taken to address any resource gaps or imbalances observed in the last sprint?
8. Have any adjustments or improvements been initiated based on the Planned vs Actual chart to make use of resource allocation in future sprints?
9. Are there any lessons learned from the last sprint that can be applied to improve planning and execution in upcoming sprints?
10. What measures are being taken to ensure better flow between the planned and actual counts in future sprints?

## Risk Management Matrix
RISK MANAGEMENT MATRIX
IMPACT
|  | 1 - Very Low | 2 - Low | 3 - Medium | 4 - High | 5 - Very High
LIKELIHOOD | 5 - Very High
4 - High
3 - Medium
2 - Low
1 - Very Low