## Slide 1
End of Sprint (Highlight) Report
1. Progress Update this reporting period | 2. Objectives for next reporting period
The project is focusing on design-related backlog items during this sprint, while customer experience-related items have been pushed to the next sprint. Store location development is complete, and finance reporting work is planned for the next sprint The project is focusing on design-related backlog items during this sprint, while customer experience-related items have been pushed to the next sprint. Store location development is complete, and finance reporting work is planned for the next sprint The Developers have expressed concerns about information security development, as they lack expertise in this area and have requested guidance Development has been impacted by two developers lacking licenses for key development tools, causing some backlog items to be delayed until the next sprint | Complete development and testing of backlog items for the App Refresh project, ensuring compliance with information security requirements Resolve the resource allocation issue with the UX/UI team for the Website Refresh project. Provide guidance to the Developers regarding information security development
3. Key Meetings and Decisions Required | 4. Escalated Issues and Risks (More detail available in logs)
Meeting with the Audit Lead to discuss plans for managing data protection and information security, ensuring compliance with rules regulations. Meeting with the Audit Lead to discuss plans for managing data protection and information security, ensuring compliance with regulations. | Title & Owner The Audit Lead has raised concerns about non-compliance with data protection and information security regulations across multiple projects within the Ecommerce domain. Failure to comply may result in penalties. A meeting with the Audit Lead is required to discuss the plans in place and ensure information security-related development is completed before the external audit in two weeks
Project Name | App Refresh project,Website Refresh project
Project Manager | Farai Thando Mhlabi
Date | 20/05/2023
RAG Status |  | Overall |  | Scope | Resource | Timelines | Costs
This Sprint |  | GREEN |  | GREEN | AMBER | AMBER | GREEN

## Slide 2: RAG Definition For Project Status
Private & Confidential
RAG Status | Green | Amber | Red
Scope | Clear on deliverables Clear on what's in/out of scope Interdependencies with other projects/activities understood and being managed | Major deliverables clear but scope still moving/lack of clarity (including change requests not yet approved) Plan in place to address | Significant uncertainty in scope and deliverables
Resource | Project team in place, no significant gaps in resourcing No risk to project delivery | Gap in resourcing but plan in place to address Project delivery at risk but manageable | Resource not in place/ roles not identified Impact on ability to deliver project
Timelines | Clear on timelines/critical path On track to deliver to milestones | Timeline slipping against planned dates although not yet missed any key project milestones that would result in a delay in project completion Plans in place to mitigate risk and stakeholders aware | Progress has slipped behind plan to the point that delivering the overall project on schedule is not recoverable without intervention
Costs | Costs clearly defined and corresponding budget allocated to the project Project forecast to be on track/under budget | Remaining uncertainty about costs Budget identified but not yet signed off Project is projecting to overspend and there is a risk that they may seek approval for additional funding | Costs not understood Budget not available Project has overspent or there is a high likelihood of the risk of overspend.
Overall | No Red sub-categories No more than 1 Amber sub-category with clear plan to bring back to Green No risk or issue material to project success | No Red sub-categories More than 1 Amber sub-category Risks and issues exist with plans to manage them | One or more Red sub-category Significant risk or issue without appropriate treatment plan