## HLP_ Project HotelO24
Project HotelO24 - High Level Plan (HLP)
| KEY: |  | Task/Milestone COMPLETE
Task/Milestone LATE
Task/Milestone AT RISK
Task/Milestone ON TRACK
CURRENT YEAR
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Pre project
Project Mandate | bar: Q1 Month 1
Design & Specifications Stage
Construction Plans & Specifications Signed Off | bar: Q1 Month 2
Safety Certificates Obtained | bar: Q1 Month 3
Construction & Build Stage
Build - Building Contractors On Site | bar: Q1 Month 2 to Q4 Month 11
Site Complete | bar: Q4 Month 12
Site Commissioning Stage
Site Handover Complete | bar: Q1 Month 1
Hotel Chain Move onto Site - Pre Launch Preparation | bar: Q1 Month 1 to Q1 Month 3
Hotel Chain Pre Launch Preparation Completes | bar: Q2 Month 4
Project Closure | bar: Q2 Month 5
Hotel Launch - GO LIVE | bar: Q2 Month 5
OLYMPIC GAMES DATE | bar: Q3 Month 7

## HLP_Gymnasium Project
Gymnasium Project - High Level Plan (HLP)
| KEY: |  | Task/Milestone COMPLETE
Task/Milestone LATE
Task/Milestone AT RISK
Task/Milestone ON TRACK
CURRENT YEAR
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Pre project
Project Mandate | bar: Q1 Month 1
Construction & Build Stage
Build - Building Contractors On Site | bar: Q1 Month 2 to Q3 Month 8
Main Gymnasium Site Complete | bar: Q3 Month 8
Main Gymnasium Exterior Complete | bar: Q3 Month 9
Site Commissioning Stage
Equipment Ordered and in Place | bar: Q3 Month 9 to Q4 Month 10
Equipment Testing Complete | bar: Q4 Month 10
Site Handover Complete | bar: Q4 Month 11
Sub Project Requirements
International Gym Team Requirements Agreed | bar: Q1 Month 2
International Gym Team Scope Known | bar: Q1 Month 3
Gymnasium Open for Business - GO LIVE | bar: Q2 Month 5
Project Closure | bar: Q2 Month 5
OLYMPIC GAMES DATE | bar: Q3 Month 7

## Combined Project Team Budget
Combined Project Team Resource Budget
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Internal (Consultancy) Resource
Project Manager | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 4000 | 4000 | 4000 | 88000
Operations Manager | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 108000
Design Lead | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000
Tech Lead | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 2125 | 2125 | 2125 | 2125 | 2125 | 2125 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 4250 | 89250
Internal (Consultancy)Resource Sub Total | 17250 | 17250 | 17250 | 17250 | 17250 | 17250 | 10625 | 10625 | 10625 | 10625 | 10625 | 10625 | 12750 | 12750 | 12750 | 12750 | 12750 | 12750 | 12750 | 8750 | 8750 | 12750 | 12750 | 12750 | 312250
External Resource
Building Contractors | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 100000 | 100000 | 100000 | 50000 | 50000 | 50000 | 25000 | 25000 | 0 | 400000 | 400000 | 400000 | 6500000
Site Manager | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 72000
External Resource Sub Total | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 403000 | 103000 | 103000 | 103000 | 53000 | 53000 | 53000 | 28000 | 28000 | 3000 | 403000 | 403000 | 403000 | 6572000
Resource Total | 420250 | 420250 | 420250 | 420250 | 420250 | 420250 | 413625 | 413625 | 413625 | 413625 | 413625 | 413625 | 115750 | 115750 | 115750 | 65750 | 65750 | 65750 | 40750 | 36750 | 11750 | 415750 | 415750 | 415750 | 6884250
Contingency
10% of Total Resource Budget | 42025 | 42025 | 42025 | 42025 | 42025 | 42025 | 41362.5 | 41362.5 | 41362.5 | 41362.5 | 41362.5 | 41362.5 | 11575 | 11575 | 11575 | 6575 | 6575 | 6575 | 4075 | 3675 | 1175 | 41575 | 41575 | 41575 | 688425
Resource Total Including Contingency | 462275 | 462275 | 462275 | 462275 | 462275 | 462275 | 454987.5 | 454987.5 | 454987.5 | 454987.5 | 454987.5 | 454987.5 | 127325 | 127325 | 127325 | 72325 | 72325 | 72325 | 44825 | 40425 | 12925 | 457325 | 457325 | 457325 | 7572675