## 3) Risk Log(Gymnasium)
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 | Q1 | There is not enough time for incorporating changes for new gymnastics events: Since this requires layout and setup, it can be detrimental to the project scope. | 4 | 3 | 12 | Assess the impact of the upcoming events on the existing design and plans. Identify necessary modifications with the gym committee and design team. Adapt the layout and set up to accommodate the ongoing events | Q2 | Gym Committee Member | The committee meber has to be more careful not to suffocate the project and allow scope creep
R002 | Q1 | Participants were not fully aware of the requirements for the participant team: It is the best practice that the project manager to communicate effectively with all stakeholders and fully understand project requirements | 3 | 3 | 9 | Get in touch with the UK and China teams to obtain their requirements promptly. Collaborate with the Gym Committee Member to ensure all team requirements are collected. Establish a separate sub-project to manage team areas and changing rooms. Within two weeks, develop a business case, seek funding, and obtain approval. | Q2 | Project Manager | One thing that the Project manager has to keep in mind is, avoiding gold plating hence this will jeopardize the credibility of the project
R003 | Q1 | Insufficient time for equipment ordering and design of team areas: The original plan to import trees from Japan has encountered shipping issues, reducing the available time. Plan B needs to be agreed upon and find another supplier. | 3 | 3 | 9 | Speed up the process of obtaining all the team requirements and measurements. Engage with the design lead and operations lead to finalize the design and layout. Collaborate with suppliers to ensure timely equipment ordering. Monitor progress closely to ensure completion within 6 weeks | Q2 | Project Manager | As the project manager you should always have a contigent plan and encounter Unknown Unknows
R004 | Q1 | Delay in obtaining safety certificate for the hotel terrace: The Building Surveyor has not confirmed the safety elements of the terrace, which is considered non-negotiable by the hotel chain. If this issue is not resolved urgently, the hotel may take legal action | 4 | 2 | 8 | Prioritize immediate attention to resolving the terrace safety elements. Allocate resources and engage expertise to expedite safety certification. Communicate with the building surveyors and involve them in addressing this issue promptly. | Q2 | Operations Manager | It is crucial to obtain all necessary documents to avoid delays in projection initiations
R005 |  | Lack of construction site management expertise due to the Site Manager's depature: The current Site Manager has resigned, and their knowledge and experience are critical to the project. The site may become inappropriate without a replacement and delay the whole project | 4 | 3 | 12 | Assess the available budget and explore the possibility of recruiting a contractor as a temporary replacement. Collaborate with the Operations Manager to discuss recruitment options and speed up the hiring process. Ensure knowledge transfer from the departing Site Manager to the replacement. | Q2 | Operations Manager | Inform the relevant stakeholders, such as project managers, superiors, or human resources, about the departure of the Site Manager and the potential consequences for the project. This will help raise awareness of the issue and prompt appropriate actions.
R006 |  |  |  |  | 0
R007 |  |  |  |  | 0
R008 |  |  |  |  | 0
R009 |  |  |  |  | 0
R010 |  |  |  |  | 0
R011 |  |  |  |  | 0
R012 |  |  |  |  | 0
R013 |  |  |  |  | 0
R014 |  |  |  |  | 0
R015 |  |  |  |  | 0
R016 |  |  |  |  | 0
R017 |  |  |  |  | 0
R018 |  |  |  |  | 0
R019 |  |  |  |  | 0
R020 |  |  |  |  | 0
R021 |  |  |  |  | 0
R022 |  |  |  |  | 0
R023 |  |  |  |  | 0
R024 |  |  |  |  | 0
R025 |  |  |  |  | 0

## 3) Risk Log(HotelO24)
RISK LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Impact Rating (Enter 1-5) | Likelihood Rating (Enter 1-5) | Risk Score (Impact x Likelihood) | Action & Owner (What needs to happen to mitigate this risk or is it acceptable to do nothing at this stage?) | Target Action Completion Date (When will actions be completed by?) | Risk Owner (Who is responsible for mitigating this risk?) | Any Additional Comments / Any Escalation Required?
R001 | Q1 | Building surveyor reports and timeline: The Hotel Manager is waiting for the latest reports from the Building Surveyors to assess the build timeline. The status of the project, including the completion of the gymnasium, is crucial for the hotel's planned opening six weeks before the launch. | 4 | 3 | 12 | Engage with the Building Surveyors to speed up the delivery of the reports. Ensure clear communication regarding the project's timeline and the importance of timely completion of the gymnasium | Q1 | Project Manager | Regular follow-up to ensure that the gymnasium's completion goes with the planned opening of the hotel. Any potential delays should be addressed inorder to minimize the impact on the project timeline.
R002 | Q1 | Commercial agreement with the IOC: The Hotel Manager's boss has requested an update on the commercial agreement between the hotel chain and the IOC regarding the use of the hotel after the games. The status of the agreement, currently with the IOC legal team, requires some clarification | 3 | 2 | 6 | Maintain regular contact with the IOC legal team to receive updates on the agreement's status. Seek clarification on any outstanding issues or concerns to expedite the process. | Q1 | Hotel Manager's boss | Open and transparent communication with the IOC legal team is crucial to ensure the timely completion of the commercial agreement. Address any potential roadblocks to avoid unnecessary delays
R003 | Q1 | Recruitment and staff induction: The Hotel Manager plans to bring new recruits on-site in month 8, as per the High-Level Plan, for induction and training. The timely setup and preparation for the staff's arrival are necessary for a smooth transition. | 4 | 3 | 12 | Develop a detailed recruitment plan, including timelines for advertising, selection, and hiring processes. Ensure that the site is prepared for the arrival of new recruits by setting up necessary infrastructure and organizing training materials. | Q3 | HR Manager | Adequate preparation and coordination are vital to ensure a smooth transition for new staff members. Timely hiring, effective induction processes, and a supportive work environment will contribute to their successful integration into the team.
R004 |  |  |  |  | 0
R005 |  |  |  |  | 0
R006 |  |  |  |  | 0
R007 |  |  |  |  | 0
R008 |  |  |  |  | 0
R009 |  |  |  |  | 0
R010 |  |  |  |  | 0
R011 |  |  |  |  | 0
R012 |  |  |  |  | 0
R013 |  |  |  |  | 0
R014 |  |  |  |  | 0
R015 |  |  |  |  | 0
R016 |  |  |  |  | 0
R017 |  |  |  |  | 0
R018 |  |  |  |  | 0
R019 |  |  |  |  | 0
R020 |  |  |  |  | 0
R021 |  |  |  |  | 0
R022 |  |  |  |  | 0
R023 |  |  |  |  | 0
R024 |  |  |  |  | 0
R025 |  |  |  |  | 0

## 4) Issue Log
ISSUE LOG
Risk ID | Date Raised | Description (Cause & Effect - Clearly describe what the issue is and what it is impacting - time, budget or quality) | Impact Rating (Enter 1-5) | Issue RAG | Action & Owner (What needs to happen to resolve this issue?) | Target Action Completion Date (When will actions be completed by?) | Issue Owner (Who is responsible for resolving this issue?) | Any Additional Comments / Any Escalation Required?
I001 | Q1 | Delayed Reports from Building Surveyors: Reports from the Building Surveyors have not been received or reviewed. Lack of information regarding the build timeline and completion status, specifically concerning the rooftop terrace | 4 | 4 | Project Manager: needs to address the resource gaps, particularly the shortage of Building Surveyors, and consider expanding the team to ensure smooth project execution. | Q2 | Building Surveyors | Timely receipt of reports is crucial to assess the project's progress and address any potential delays or unresolved issues.
I002 | Q1 | Uncertain Commercial Agreement with the IOC: The commercial agreement between the hotel chain and the IOC is still with the IOC legal team. Lack of clarity on post-games hotel use and potential implications for marketing and promotion. | 3 | 3 | Project Manager: Follow up with the IOC legal team to obtain an update on the agreement | Q2 | Hotel Manager's boss | Open and transparent communication with the IOC legal team is necessary to ensure timely resolution of the agreement and alignment with marketing plans.
I003 | Q1 | Recruitment and Staff Induction: The Hotel Manager plans to bring new recruits on site for induction and training in month 8, as per the High-Level Plan and there is Lack of necessary staff for the smooth transition and operation of HotelO24 | 4 | 4 | Hotel Manager: Consider recruiting a contractor quickly as a temporary replacement. | Q2 | Operations Manager | There is need to maintain effective management and mitigate potential delays or disruptions
I004 | Q1 | Contractor's Threat of Strike: Local building contractors are threatening a strike due to pay and conditions disputes. A strike could delay construction activities, leading to project delays and potential cost overruns | 3 | 3 | Operations Manager: Address contractor concerns and negotiate an agreement to prevent a strike | Q2 | Project Manager | Swift action is necessary to resolve the labor dispute and maintain construction progress without interruptions
I005 | Q1 | Design Changes and Alternative Suppliers: Issues with importing trees from Japan and Brexit-related challenges with importing gym equipment. Potential delays and the need for alternative solutions and suppliers | 3 | 3 | Operations Manager: Identify alternative suppliers and finalize arrangements within the next few weeks | Q2 | Project Manager | Suggesting a resolution and adaptation to design changes and supplier challenges is crucial to avoid further delays and ensure project continuity.
I006 | Q1 | Safety Certification for Terrace at HotelO24: The safety elements of the terrace overlooking the Olympic Stadium and grounds have not been confirmed. Hotel chain threatening legal action if the terrace is not built. | 4 | 4 | Project Manager: Urgent attention and resolution required to obtain the safety certificate | Q2 | Project Manager | The project manager needs to prioritize resolving this issue with the Building Surveyors and ensure the safety certificate for the terrace is obtained.
I007 | Q1 | Changes Required for Hotel Conversion to Residential Accommodation: The need to estimate the additional cost required (€1,500,000) and seek approval from the hotel chain to implement the changes | 3 | 3 | Project Manager: The project manager should review the issues identified by the Building Surveyors regarding the conversion of hotel accommodation to residential units | Q2 | Project Manager | Review cost benefit analysis in regards to use of the Hotel post Olympics games.
I008 |  |  |  | 0
I009 |  |  |  | 0
I010 |  |  |  | 0
I011 |  |  |  | 0
I012 |  |  |  | 0
I013 |  |  |  | 0
I014 |  |  |  | 0
I015 |  |  |  | 0
I016 |  |  |  | 0
I017 |  |  |  | 0
I018 |  |  |  | 0
I019 |  |  |  | 0
I020 |  |  |  | 0
I021 |  |  |  | 0
I022 |  |  |  | 0
I023 |  |  |  | 0
I024 |  |  |  | 0
I025 |  |  |  | 0

## 1b) Gymnasium Team Plan Templat
Project Plan Template
| KEY: |  |  | Task/Milestone COMPLETE
Task/Milestone LATE
Task/Milestone AT RISK
Task/Milestone ON TRACK
CURRENT YEAR
| Q3 | [11 empty] | Q4 | [11 empty] | Q1 | [11 empty] | Q2 | [11 empty] | Q3
Key Milestone / Tasks | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Business Case Sign-Off | bar: Month 1 Week 1 to Month 1 Week 2
Project Initiation
Design and Planning | bar: Month 1 Week 4 to Month 2 Week 1
Procurement and Equipment Delivery | bar: Month 2 Week 1 to Month 3 Week 4
Construction and Execution | bar: Month 2 Week 3 to Month 3 Week 3
Testing and Commissioning | bar: Month 3 Week 2 to Month 3 Week 4
Snagging and Handover | bar: Month 3 Week 4

## 9) Project Manager Actions Log
ACTIONS LOG
Action ID | Date Raised | Action Description (Cause & Effect - Clearly describe what the risk is and what the impact is) | Priority of Action High - Requires Urgent Attention Medium - Requires Attention within the next 2 weeks Low - Requires Attention at a much later date | Action Owner | Any Additional Comments
A001 | Q1 | Address the safety elements of the rooftop terrace at HotelO24. The terrace safety certificate has not been confirmed, and the hotel chain has stated that the terrace is non-negotiable. Failure to address this issue may result in legal action or legal consequences and a potential delay in the hotel's opening. | High | Project Manager | Urgently engage with the Building Surveyors and relevant stakeholders to speed up the safety certification process for the terrace. Explore alternative solutions if necessary.
A002 | Q1 | Find a replacement for the Site Manager who has resigned. The absence of an experienced Site Manager could lead to project delays and a decline in site management quality. | High | Project Manager/Operations Manager | Initiate the recruitment process to find a suitable replacement. Consider options such as hiring a contractor.
A003 | Q1 | Address the potential strike threat from the building contractors. A strike by local contractors over pay and conditions could significantly impact construction progress and project timelines. | Medium | Operations Manager | Engage in negotiations with the building contractors to address their concerns and find a resolution. Consider involving external experts with experience in overseas trade union matters if necessary
A004 | Q1 | Develop a Plan B for the external aspects of the gymnasium due to shipping issues with the trees from Japan. Inability to import the trees from Japan may impact negatively on the desired theme of the gymnasium. | Low | Design Lead/Project Manager | Explore alternative suppliers or local options for trees or landscaping features that align with the desired project plan. Ensure that any alternative plan is approved by relevant stakeholders.
A005 | Q1 | Monitor and address import/export challenges for gym equipment due to Brexit. Brexit-related import/export challenges may cause delays or complications in the delivery of gym equipment. | Medium | Procurement Specialist/Project Manager | Stay in close communication with suppliers and shipping agents to navigate any import/export challenges. Consider alternative suppliers or explore other shipping options if required
A006
A007
A008
A009
A010
A011
A012
A013
A014
A015
A016
A017
A018
A019
A020
A021
A022
A023
A024
A025

## Risk Management Matrix
RISK MANAGEMENT MATRIX
IMPACT
|  | 1 - Very Low | 2 - Low | 3 - Medium | 4 - High | 5 - Very High
LIKELIHOOD | 5 - Very High
4 - High
3 - Medium
2 - Low
1 - Very Low