## Slide 1
Project Status (Highlight) Report
1. Progress Update this reporting period | 2. Objectives for next reporting period
During this reporting period, significant progress was made on the Gymnasium Project. The construction activities are on track, and the team successfully completed the foundation work and structural framing. The installation of mechanical, electrical, and plumbing systems are on the right track, and the project remains within the planned budget. | Complete the installation of mechanical, electrical, and plumbing systems Begin interior finishing work, including flooring, painting, and fixtures Initiate landscaping and outdoor area development Conduct regular inspections to ensure compliance with safety regulations Coordinate with the Gym Committee to address any updated requirements
3. Key Meetings and Decisions Required | 4. Escalated Issues and Risks (More detail available in logs)
Meeting with the Gym Committee to discuss the additional requirements resulting from the new gymnastics events and finalize the layout and set up accordingly Meeting with the Building Surveyors to address the safety certificate for the terrace and confirm the necessary actions for compliance | Title & Owner Risk: Delay in obtaining safety certificate for the hotel terrace, which may impact the hotel chain's legal obligations and potential legal action Risk: Insufficient availability of skilled labor for the interior finishing work, which may lead to schedule delays and increased costs. Issue: Lack of clarity regarding the requirements from the UK and China gymnastics teams, which affects the design and layout of their respective team areas Issue: Potential impact on timeline and costs due to Brexit-related challenges in importing gym equipment from the UK and US.
Project Name | Gymnasium Project
Project Manager | Farai Thando Mhlabi
Date | 31/05/2023
RAG Status |  | Overall |  | Scope | Resource | Timelines | Costs
This period |  | GREEN |  | AMBER | GREEN | AMBER | GREEN

## Slide 2
Project Status (Highlight) Report
RAG Status |  | Overall |  | Scope | Resource | Timelines | Costs
This period |  | AMBER |  | GREEN | GREEN | AMBER | GREEN
Project Name | HotelO24 Project
Project Manager | Farai Thando Mhlabi
Date | 31/05/2023
1. Progress Update this reporting period | 2. Objectives for next reporting period
The HotelO24 Project made notable progress during this reporting period. The construction is proceeding as planned, and the team successfully completed the exterior facade work and started interior fit-outs. The budget remains on track, and pre-opening activities, such as staff recruitment, are underway | Finalize interior fit-outs, including room furnishings, fixtures, and amenities. Complete the installation of necessary systems, such as HVAC, plumbing, and electrical. Commence testing and commissioning of all building systems. Address the safety elements of the rooftop terrace as per the hotel chain's requirements. Obtain updates on the commercial agreement between the hotel chain and the IOC for post-games usage.
3. Key Meetings and Decisions Required | 4. Escalated Issues and Risks (More detail available in logs)
Meeting with the Building Surveyors to discuss the safety elements of the rooftop terrace and ensure necessary actions are taken to meet the hotel chain's requirements. Follow-up with the IOC legal team to obtain updates on the commercial agreement for post-games usage. | Title & Owner Risk: Potential delay and legal implications if the safety elements of the rooftop terrace are not confirmed and constructed as per the hotel chain's requirements. Risk: Possible strike by the building contractors due to disputes over pay and conditions, which may impact construction progress. Issue: Brexit-related challenges in importing gym equipment, potentially affecting the timeline and costs

## Slide 3: RAG Definition For Project Status
Private & Confidential
RAG Status | Green | Amber | Red
Scope | Clear on deliverables Clear on what's in/out of scope Interdependencies with other projects/activities understood and being managed | Major deliverables clear but scope still moving/lack of clarity (including change requests not yet approved) Plan in place to address | Significant uncertainty in scope and deliverables
Resource | Project team in place, no significant gaps in resourcing No risk to project delivery | Gap in resourcing but plan in place to address Project delivery at risk but manageable | Resource not in place/ roles not identified Impact on ability to deliver project
Timelines | Clear on timelines/critical path On track to deliver to milestones | Timeline slipping against planned dates although not yet missed any key project milestones that would result in a delay in project completion Plans in place to mitigate risk and stakeholders aware | Progress has slipped behind plan to the point that delivering the overall project on schedule is not recoverable without intervention
Costs | Costs clearly defined and corresponding budget allocated to the project Project forecast to be on track/under budget | Remaining uncertainty about costs Budget identified but not yet signed off Project is projecting to overspend and there is a risk that they may seek approval for additional funding | Costs not understood Budget not available Project has overspent or there is a high likelihood of the risk of overspend.
Overall | No Red sub-categories No more than 1 Amber sub-category with clear plan to bring back to Green No risk or issue material to project success | No Red sub-categories More than 1 Amber sub-category Risks and issues exist with plans to manage them | One or more Red sub-category Significant risk or issue without appropriate treatment plan